## Risk_Register
Risk ID | Risk Description | Asset/Process | Threat | Vulnerability | Likelihood | Impact | Risk Rating | Existing Control | Recommended Treatment | Risk Owner | Status
RSK-01 | Legacy VPN portal lacks mandatory Multi-Factor Authentication (MFA). | Remote Access / VPN | Credential stuffing / Brute force attack | Missing MFA enforcement on legacy admin portal | 3 | 3 | High (9) | Password policy (12 chars) | Mitigate: Enforce conditional access MFA via Entra ID within 14 days. | IT Lead | Open
RSK-02 | Terminated employees retain Active Directory & AWS access for up to 5 days post-exit. | Entra ID / AWS Console | Insider threat / Unauthorized data extraction | Manual offboarding process without HR-IT integration | 3 | 3 | High (9) | HR sends weekly termination emails | Mitigate: Automate JML offboarding script via HRMS triggers within 24h of exit. | HR & IT Lead | Open
RSK-03 | Cloud Storage (AWS S3) containing database backups lacks lifecycle retention/deletion rules. | AWS S3 Buckets | Regulatory non-compliance (GDPR/DPDPA right to erase) | Unmanaged backup retention policies | 2 | 3 | High (6) | Manual periodic cleanup | Mitigate: Implement automated lifecycle policy (purge after 90 days). | DevOps Lead | Open
RSK-04 | Centralized SIEM logs (AWS CloudTrail) auto-delete after 30 days due to storage constraints. | AWS CloudTrail / SIEM | Unauthorized activity goes undetected; incident investigation fails | Default log retention settings | 2 | 3 | High (6) | 30-day cloud logging | Mitigate: Export logs to immutable, encrypted S3 bucket with 365-day retention. | SecOps Lead | Open
RSK-05 | Production database containing payroll PII accessed directly by 6 developers via shared credentials. | Production RDS Database | Unauthorized PII exposure; lack of attribution | Excessive privileges & shared DBA accounts | 3 | 3 | High (9) | IP Whitelisting | Mitigate: Implement RBAC, individual accounts, and Bastion access with logging. | DevOps Lead | Open
RSK-06 | Third-party background verification vendor has no documented SOC 2 or ISO 27001 report on file. | Vendor Management | Vendor data breach exposing candidate personal data | Missing Vendor Risk Management (VRM) policy | 2 | 2 | Medium (4) | NDA signed at onboarding | Mitigate: Conduct vendor security questionnaire and request SOC 2 Type II report. | GRC Analyst | Open
RSK-07 | Incident Response Plan has not been updated or tested in over 18 months. | Incident Response | Delayed response to security breach leading to compliance fines | Outdated playbooks and unassigned IR roles | 2 | 3 | High (6) | Outdated IR PDF on SharePoint | Mitigate: Update IR Plan with DPDPA/GDPR breach notification timelines & hold tabletop exercise. | Security Lead | Open
RSK-08 | Lack of explicit consent logging mechanism for processed personal data of Indian citizens. | Customer Portal / App | Regulatory fine under India DPDPA Section 6 | Missing consent management module | 3 | 2 | High (6) | Generic Terms & Conditions checkbox | Mitigate: Deploy granular consent manager with log tracking for processing purpose. | Product Lead | Open