## Remediation Roadmap
Phase | Timeframe | Priority Level | Action Item / Control Remediation | Responsible Owner | Target Deliverable
Phase 1 | Immediate (0–30 Days) | High | Fix MFA Blindspot: Enforce Entra ID Conditional Access MFA on legacy VPN endpoints. | IT Operations | Conditional Access Policy screenshot & MFA enforcement report.
Phase 1 | Immediate (0–30 Days) | High | Revoke Direct Database Access: Remove direct DB credentials for developers and route access through Teleport/Bastion proxy. | DevOps Lead | Bastion access config & updated DB user permission audit log.
Phase 1 | Immediate (0–30 Days) | High | Emergency Offboarding Audit: Execute PowerShell/AD script to disable all stale accounts for staff terminated >7 days ago. | HR & IT Ops | Active Directory disabled accounts log report signed by IT Lead.
Phase 2 | Short-Term (31–90 Days) | High | Automate JML Offboarding: Deploy HRMS-to-Active Directory webhooks for instant account disablement on exit trigger. | HR & IT Ops | Functional automated integration test log & updated JML SOP.
Phase 2 | Short-Term (31–90 Days) | Medium | Extend Cloud Log Retention: Configure AWS CloudTrail & application S3 buckets to retain encrypted logs for 365 days in Glacier. | DevOps Lead | S3 Lifecycle Configuration screenshot & backup encryption verification.
Phase 2 | Short-Term (31–90 Days) | Medium | Establish Incident Notification SLAs: Update Incident Response Plan to include 72h GDPR and 6h CERT-In breach reporting. | SecOps Lead | Approved IR Policy document v2.0 & tabletop exercise agenda.
Phase 3 | Medium-Term (91–180 Days) | Medium | Vendor Risk Assessment Program: Collect & review VRM questionnaires and SOC 2 Type II reports from key SaaS suppliers. | GRC Analyst | Completed Vendor Risk Tracker & Vendor SOC 2 archive folder.
Phase 3 | Medium-Term (91–180 Days) | Low | Automate Data Retention Purge: Deploy DB scripts to delete/anonymize inactive personal data exceeding retention limits. | Data Protection Officer | SQL deletion job logs & Data Lifecycle execution report.